## Tasks and Timeline
Sauce & Spoon Project Plan
| Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone 1: Tablet Research
1.1 | Research tablet customization options | estimation dates from historical data |  |  | 4
1.3 | General quotes and review costs |  |  |  | 3
1.4 | Test out tablets |  |  |  | 4
1.5 | Choose a tablet system |  |  |  | 4
1.6 | Provide Pilot Restaurant installation layouts to Seydou for wiring |  |  |  | 0
1.7 | Marketing team works with vendors to design look of tablets |  |  |  | 10
1.8 | Vendor timeline and deliverables schedule concerning installation/wiring | estimation dates from historical data |  |  | 4
Milestone 2: Planning
2.1 | Create contracts and the SoW for vendor | estimation dates from historical data |  |  | 3
2.2 | Update stakeholders on launch date |  |  |  | 0
2.3 | Project Plan Updates |  |  |  | 13
2.4 | Update marketing/social media/etc. |  |  |  | 10
2.5 | Create launch day plan |  |  |  | 7
Milestone 3: Tablet Customization/Shipping/Installation
3.1 | Confirm compatible operating system with existing POS |  |  |  | 0
3.2 | Check on POS version status | if POS software is out of date, we need to update software first to make compatible with tablets. |  |  | 4
3.3 | Determine how many tablets we need to order for each location |  |  |  | 8
3.4 | Menu revamp to feature with pilot rollout |  |  |  | 7
3.5 | Confirm the number of devices needed for both locations |  |  |  | 5
3.6 | Follow-up with Carter on menu |  |  |  | 0
3.7 | Confirm mock-up designs with Deanna and Carter |  |  |  | 0
3.8 | Send menu and coupon mock-ups to marketing/vendors for upload into tablets. |  |  |  | 0
3.9 | Confirm and finalize tablet design |  |  |  | 0
3.1 | Finalize order of tablets |  |  |  | 1
3.11 | Book electrician for specific dates |  |  |  | 0
3.12 | Tablets shipping from warehouse | if devices are broken, vendor will expedite overnight shipping. Update: new devices are delayed due to major storms overseas, so going to order current tablets and have upgrades installed a month after launch. Current devices available in out-of-state warehouse, meaning an additional 3-4 days shipping. |  |  | 12
3.13 | Confirm shipment of tablets |  |  |  | 3
3.14 | Electrician arrives for wiring | 2 business days, can't close restaurants schedule 2 half-days |  |  | 7
3.15 | Tablet installation at North location |  |  |  | 2
3.16 | Tablet installation at Downtown location |  |  |  | 2
3.17 | Tablet integration with existing POS |  |  |  | 0
3.18 | Test tablets to make sure no problems |  |  |  | 1
3.19 | Troubleshoot if necessary |  |  |  | 3
Milestone 4: Staff training
4.1 | Follow-up with Gilly and Alex about staff meeting scheduling |  |  |  | 0
4.2 | Pre-training staff meeting at North location to introduct tablets | introduce tablets and changes to staff |  |  | 0
4.3 | Pre-training staff meeting at Downtown location to introduce tablets |  |  |  | 0
4.4 | Coordinate with Gilly and Alex to schedule staffing training at each location. | Each part of the training (pre-training, manager training, staff training) will take place on different days. |  |  | 0
4.5 | Set a date for staff training at each location and update staff calendars |  |  |  | 0
4.6 | Start drafting a training plan |  |  |  | 10
4.7 | Confirm training dates with Gilly and Alex |  |  |  | 0
4.8 | Preparation and planning for the training |  |  |  | 10
4.9 | Train GMs on new tablets with Seydou | Seydou will train, 2 hours for each training plus one hour before and after each training for facilitator prep/debrief |  |  | 2
4.1 | Alex trains the Downtown staff |  |  |  | 2
4.11 | Gilly trains the North staff |  |  |  | 2
4.12 | Train staff with real-life updates on office computer |  |  |  | 2
Milestone 5: Testing/troubleshoot
5.1 | Test-run of tablets in restaurants |  |  |  | 2
5.2 | Create troubleshoot plan/support plan | estimation date from historical data |  |  | 5
5.3 | Launch day | estimation date from historical data |  |  | 0
5.4 | Installation of upgraded devices after launch day |  |  |  | 2

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone 1: Tablet Research
Research tablet customization options | estimation dates from historical data | 4 |  |  |  | H
General quotes and review costs |  | 3 |  |  |  | H
Test out tablets |  | 4 |  |  |  | H
Choose a tablet system |  | 4 |  |  |  | H
Provide Pilot Restaurant installation layouts to Seydou for wiring |  | 0
Marketing team works with vendors to design look of tablets |  | 10 | 1 week | 10 days | 3 weeks
Vendor timeline and deliverables schedule concerning installation/wiring | estimation dates from historical data | 4 |  |  |  | H
Milestone 2: Planning
Create contracts and the SoW for vendor | estimation dates from historical data | 3 |  |  |  | H
Update stakeholders on launch date |  | 0 |  |  |  | H
Project Plan Updates |  | 13 |  |  |  | H
Update marketing/social media/etc. |  | 10 |  |  |  | H
Create launch day plan |  | 7 |  |  |  | H
Milestone 3: Tablet Customization/Shipping/Installation
Confirm compatible operating system with existing POS |  | 0 | 1 hour | 3 hours | 5 hours
Check on POS version status | if POS software is out of date, we need to update software first to integrate with tablets. | 4 | 3 days | 4 days | 4 days | H
Determine how many tablets we need to order for each location |  | 8 | 1 week | 7 days | 3 weeks
Menu revamp to feature with pilot rollout |  | 7 | 1 week | 7 days | 2 weeks
Confirm the number of devices needed for both locations |  | 5 | 1 day | 1 week | 2 weeks | M
Follow-up with Carter on menu |  | 0
Confirm mock-up designs with Deanna and Carter |  | 0
Send menu and coupon mock-ups to vendors for upload into tablets. |  | 0 | 3 hours | 4 hours | 4 hours | H
Confirm and finalize tablet design |  | 0
Finalize order of tablets |  | 1 | 1 hour | 1 day | 2 days
Book electrician for specific dates |  | 0
Tablets shipping from warehouse | if devices are broken, vendor will expedite overnight shipping. Update: new devices are delayed due to major storms overseas, so going to order current tablets and have upgrades installed a month after launch. Current devices available in out-of-state warehouse, meaning an additional 3-4 days shipping. | 12 | 10 days | 12 days | 14 days
Confirm shipment of tablets |  | 3 | 1 day | 3 days | 1 week
Electrician wires pilot locations | 2 business days, can't close restaurants schedule 2 half-days | 7 | 4 days | 7 days | 10 days | M
Tablet installation at North location |  | 2 | 1 day | 2 days | 4 days
Tablet installation at Downtown location |  | 2 | 1 day | 2 days | 4 days
Tablet integration with existing POS |  | 0 | 3 hours | 4 hours | 4 hours | L
Test tablets to make sure no problems |  | 1 | 3 hours | 5 hours | 1 day
Troubleshoot |  | 3 | 1 day | 3 days | 1 week
Milestone 4: Staff training
Follow-up with Gilly and Alex about staff meeting scheduling |  | 0
Pre-training staff meeting at North location to introduct tablets | introduce tablets and changes to staff | 0 | 1 hour | 2 hours | 3 hours | H
Pre-training staff meeting at Downtown location to introduce tablets |  | 0 | 1 hour | 2 hours | 3 hours | H
Coordinate with Gilly and Alex to schedule staffing training at each location. | Each part of the training (pre-training, manager training, staff training) will take place on different days. | 0 | 1 day | 5 days | 2 weeks | H
Set a date for staff training at each location and update staff calendars |  | 0 |  |  |  | H
Start drafting a training plan |  | 10 | 1 week | 9 days | 3 weeks
Confirm training dates with Gilly and Alex |  | 0 |  |  |  | H
Preparation and planning for the training |  | 10 | 1 week | 2 weeks | 3 weeks | M
Train GMs on new tablets with Seydou | Seydou will train, 2 hours for each training plus one hour before and after each training for facilitator prep/debrief | 2 | 4 hours | 6 hours | 1 week, 6 hours | H
Alex trains the Downtown staff |  | 2 | 4 hours | 6 hours | 1 week, 6 hours | M
Gilly trains the North staff |  | 2 | 4 hours | 6 hours | 1 week, 6 hours | M
Train staff with real-life updates on office computer |  | 2 | 4 hours | 6 hours | 1 week, 6 hours | L
Milestone 5: Testing/troubleshoot
Test-run of tablets in restaurants |  | 2 | 1 day | 2 days | 3 days | M
Create troubleshoot plan/support plan | estimation date from historical data | 5
Launch day | estimation date from historical data | 0
Installation of upgraded devices after launch day |  | 2 | 1 day | 2 days | 4 days

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Possible Tasks for launching a tabletop tablet restaurant project | https://www.linkedin.com/pulse/possible-tasks-launching-tabletop-tablet-restaurant-project-irodinjo/ | 2023-10-30 | Phenomenal list of tasks
Best uses for tablets at your restaurant | https://www.business.com/articles/best-tablet-uses-restaurants/ | 2023-10-30 | Great article on benefits of adding to/switching over to tablet menu with best practices

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer satisfaction | average ticket time - the amount of time between placing an order and delivering the order - 8 mins for appetizers, 12-15 mins for entrees. | Are the waitstaff hearing complaints from customers concerning ticket time? |  | FALSE
Ease of use | quicker checkout time - mirror the online delivery checkout system. Ensure a seamless process and ease of navigation. Measure - 1 minute checkout time | Are the customers finding the payment system quick and easy to use? | table turnover time is decreasing towards the 30 minute goal. | FALSE
Functionality | <5% of customers report technical issues each week | Are the tablets working as expected? | tablet logs report one error per shift. | FALSE
Productivity | 98% order accuracy | Are customers receiving the correct orders the first time? | avg food waste is decreased by 25% | FALSE
Effectiveness | lobby customer wait time average of 10 minutes or less. | Do the customers find that they have to wait too long to be seated? Does the hostess notice frustration amongst those waiting? | increased daily guest counts by 10% | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
average ticket time - the amount of time between placing an order and delivering the order - 8 mins for appetizers, 12-15 mins for entrees. | Are the waitstaff hearing complaints from customers concerning ticket time? |  | What age group do you belong to? | Multiple choice | 18-24 | 25-34 | 35-44 | 45-54 | 55+
quicker checkout time - mirror the online delivery checkout system. Ensure a seamless process and ease of navigation. Measure - 1 minute checkout time | Are the customers finding the payment system quick and easy to use? | table turnover time is decreasing towards the 30 minute goal. | Have you dined at Sauce & Spoon before? | Yes/No | Yes | No
<5% of customers report technical issues each week | Are the tablets working as expected? | tablet logs report one error per shift. | Did you have a chance to experience our new tabletop tablets? | Yes/No | Yes | No
98% order accuracy | Are customers receiving the correct orders the first time? | avg food waste is decreased by 25% | On a scale of 1-5 (1 = needs improvement and 5 = excellent experience) how would you rate your overall experience with the new tabletop tablets? | Scaled | 1 - needs improvement | 2 | 3 | 4 | 5 - excellent experience
lobby customer wait time average of 10 minutes or less. | Do the customers find that they have to wait too long to be seated? Does the hostess notice frustration amongst those waiting? | increased daily guest counts by 10% | Did you have any technical difficulties with the tablets? | Yes/No | Yes | No
|  |  | If you answered yes to question 5, could you list what the difficulties were? | Open-ended | open-ended
|  |  | What was your overall dining time? | Multiple choice | about 30-35 minutes | about 40-45 minutes | about 50-55 minutes | about 60-65 minutes | more than 70 minutes
|  |  | How long did you find the wait time between when your order was submitted and when you received your food to be? | Multiple choice | 8-14 minutes | 15-21 minutes | 22-28 minutes | 28-34 minutes | more than 35 minutes
|  |  | True or false, your order accuracy was correct the first time without a need to take the order back? | True/False | TRUE | FALSE
|  |  | If you answered ‘false’ to question 9 and the order accuracy was not correct, what was the problem? | Open-ended | open-ended
|  |  | True or false, your interaction with the staff at Sauce & Spoon was an enjoyable experience? | True/False | TRUE | FALSE
|  |  | If you answered ‘false’ to question 11, why was your interaction not enjoyable? | Open-ended | open-ended
|  |  | On a scale of 1-5 (1= not at all likely and 5= highly likely), how likely is it that you would recommend Sauce & Spoon to your friends and family? | Scaled | 1 - Not likely | 2 | 3 | 4 | 5 - Highly likely
|  |  | On a scale of 1-5, how likely is it that you would come back to Sauce & Spoon? | Scaled | 1 - Not likely | 2 | 3 | 4 | 5 - Highly likely
|  |  | Any other feedback you can provide concerning the new tablets, their functionality, and your overall experience? Is there anything we can do to motivate you to come visit us again? | Open-ended | open-ended